## To-Dos — List page from Classic
Action | Description | Responsible | Due Date | Complete | Comments | Last Update
A2012.09 | Map WDCPC metadata items to GAW metadata profile in collaboration with GAWSIS; share NADP metadata with GAWSIS | vb, jkl | 2013-09-30 |  | 1) vb to establish contact with Bob Larsson; 2) Bob Larsson to contact jkl and agree on exchange format | 2013-07-05
A2012.13 | Encourage review of GAW data policy (commercial use, open data license) a the appropriate level of governance, i.e., JSC OPAG EPAC | jma [from jkl] | 2013-08-30 |  | The issue was also considered at the SAG Aerosol meeting in Wessling in Oct 2012. It will be brought to the attention of JSC in March 2013.
A2013.01 | Draft of MoU will be shared once available | gb [from tc] | 2013-02-28 |  | WMO secretariat is the lead on drafting the MOUs | 2013-06-20
A2013.04 | Send letter from WMO to PRs requesting more precise coordinates of stations (suggest to use GoogleEarth gawsis.kml file as a start) | gb | 2013-08-30 |  | 1) jkl to provide gb with a table of Vol A and GAWSIS coordinates that do not match; clarification needed on station versus instrument coordinates; 2) gb to follow up by end of August;
A2013.17 | Draft a plan to organize the process for addressing dormant stations | jkl, gb | 2013-08-30 |  | Discussion with gb and Oksana took place at WMO on 4 July 2013. jkl to setup queries to address the issue in reference to the procedures foreseen in GSP Addendum p49 | 2013-07-05
A2014.04 | Revise the draft GAW metadata profile according to recommendations | JK |  |  |  | 2014-06-17
A2014.05 | Validate links between parameters and CF standard names, and submit any changes to JK for inclusion in the GAWSIS name table | All WDCs |  |  |  | 2014-06-17
A2014.06 | Submit any new names to CF | All WDCs concerned |  |  |  | 2014-06-17
A2014-07 | Prepare doc 5.4 and submit for discussion to ET-WDC | JMA |  |  | See Telecon-8 and 9. Need an extension of the presentation with clear-cut arguments pro and con DOIs. | 2014-09-02
A2014-09 | All WDCs are required to post the current GAW data policy statement, unaltered, on their respective web sites | All WDCs and GAWSIS |  |  |  | 2014-06-17
A2014-11 | Provide input for empty sections in document [refers to Doc 5.8 – Roles and responsibilities, existing collaborations, data flows ...] | WDCPC, WDCA, WRDC |  |  |  | 2014-06-17
A2014-12 | Create a mechanism for users to share conversion software | MS, JK |  |  |  | 2014-06-17
A2014-13 | Develop a GAW Data Quality Report by end of 2014 [JK to coordinate, all WDCs to contribute]. First milestone: Develop an outline based on doc 6.1, 6.2, 5.8 | JK, All WDCs |  |  |  | 2014-06-17
A2014-15 | WDC managers to share their list of metrics, ideally supported by charts, screenshots, documentation available | HK to coordinate and compile |  |  |  | 2014-06-17
A2014-16 | Confirm with Secretariat and inform ET-WDC how the Secretariat can provide support in chasing silent stations to submit their data | GB |  |  |  | 2014-06-17
A2014-19 | Describe the vision in a short paragraph to define the scope | JK
A2014-20 | Develop the strategy report (internal) as input for scoping our contributions to the next GAW Implementation Plan | TC, with contributions by all |  |  |  | 2014-06-17
A2014-22 | (1) Each WDC should investigate the availability and cost of using Digital Object Identifiers for its datasets. (2) WDCs should determine who would assign DOIs, given the different data types and complexities in each WDC. | All | 2014-09-30 |  | Discussed during telecon-9; feedback from WRDC missing. | 2014-08-29
A2014-25 | Continue discussions with Bob Vet with a goal to establish technical solution for metadata exchange with GAWSIS | VB | 2014-10-30
A2014-26 | Formulate an alternative data policy statement, taking onto account educational and policy use, also taking into account A2014-10; JK to bring this up for decision by EPAC SSC once agreed by ET-WDC | TC | 2014-09-30
A2012.08 | Update and post GAW ISO19115 profile | jkl | 2013-08-30 | on | XML files produced have been improved based on interaction with S. Starkweather (NOAA). Files have been reviewed by E. Toyoda (IPET-MDRD) and work is presently (June 2013) ongoing to incorporate his recommendations.
A2012.10 | Develop a CF profile for one wet deposition variable as an example for SAG consideration | vb | 2013-09-16 | on
A2012.11 | Agree bilaterally on WOUDC list of terms for CF | tc, jkl | 2013-07-31 | on |  | 2013-07-05
A2012.12 | Define CF names for gas variables including isotope ratios | hk | 2013-07-31 | on |  | 2013-07-05
A2012.14 | Clarify the apparent suspension of data submissions of Canadian sites to WRDC and collaborate with WRDC to find a solution | tc | 2012-10-31 | on | completed… the process for getting Canadian data into WRDC is underway. We are sorting out the details with Anatoly | 2013-06-20
A2012.15 | Identify and get in touch with Austrian lab(s) responsible for precip chem obs | jkl, vb | 2012-10-31 | on | Austrian program is suspended.
A2012.16 | Put list of action items on ET-WDC web site | jkl | 2012-10-31 | on
A2013.02 | Organise telecon on subject, involving mf and jkl | vb |  | on | subsumed in A2013.04 | 2013-07-05
A2013.03 | Establish correspondence between stations in Vol A and stations in GAWSIS [from: Propose to ET-WMD to include the GAWID in VolA] | jkl | 2013-08-30 | on | Station identifiers to be viewed in larger context of WIGOS/WIR. For now, we will attempt to include the WMO IDs in GAWSIS. Once this is firmly established, the reverse can be attempted | 2013-07-05
A2013.05 | Prepare draft document that will help focus the discussion on pros and cons of DOIs for further ET-WDC consideration [from: Telecon on DOIs] | jma [from jkl] | 2013-08-30 | on | addressed in Telecon-8; replaced with new action item | 2014-07-18
A2013.06 | Investigate WMO policy in case of unauthorised data use | gb | 2013-02-28 | on | No sanctions foreseen | 2013-06-13
A2013.07 | Create at NILU an ftp access to data so that WDCGG can harvest the data | mf | 2013-03-31 | on | EBAS serves as European node for submission to WDCGG | 2013-06-27
A2013.08 | Consider governance issue related to work flows of intermediate data centres | tc | 2013-07-31 | on | Agenda item for JMA meeting 2014 | 2013-07-05
A2013.09 | Indicate additional terms for Table 16 of WMO Core to jkl (14 Feb 2013, jkl to circulate consolidated list, then review and agreement by 22 Feb 2013) | hk | 2013-07-31 | on | based on input from meeting at JMA (hosted by Toyoda); completed during ET-WDC meeting in Tokyo 2014 | 2014-07-18
A2013.10 | Review recomandations on RoleCodes (via e-mail exchange) | jkl | 2013-08-30 | on | will be re-visited in the context of finalizing the GAW metadata profile (A2012.08) | 2014-07-18
A2013.11 | Send asap e-mail to ET-WDC detailing his thoughts on choice of metadata item "otherConstraints" (data policy, page 23 of meeting documentation) | hk |  | on
A2013.12 | Send input to jkl | all | 2013-02-22 | on | Thanks to all! | 2013-02-28
A2013.13 | Provide a few activity slides to jkl | all | 2013-02-22 | on | Thanks to all! | 2013-02-28
A2013.14 | Inform tc about situation | hk | 2013-02-28 | on | item dropped | 2014-07-18
A2013.15 | Review the questionnaire format, probably need more questions on interoperability issues | tc |  | on | yes our initial suggestion was to add questions related to interoperability…probably also need a section on data management and data quality. Also it is a good foundation for a user feedback questionnaire
A2013.16 | Request chat about process for issuing GAW IDs with jkl | tc |  | on | Bilateral telecon was held | 2013-06-13
A2013.18 | Submit additional terms for Code table 16 of WMO Core Metadata Profile v1.3 to WMO | jkl | 2013-08-30 | on | 1) hk to check that Toyoda sent input to jkl; apparently, no concerns to add 'atmosphericComposition' to table 16 of WMO_CategoryCode in the WMO core metadata profile (http://wis.wmo.int/2013/metadata/version_1-3-0/WMO_Core_Metadata_Profile_v1.3_Specification_Part_2_v1.0FINAL.pdf); 2) for radiation, jkl suggested solarRadiation, infraredRadiation and uvRadiation; 3) submit elements to WMO (to whom??); completed after ET-WDC Tokyo meeting | 2014-07-18
A2014.02 | Clarify status of submission of Japanese PFR data to WDCA | MF, HK |  | on | JMA is still working on it but the information on the situation has been shared. | 2014-09-02
A2014.03 | State the data archive hosting the data next to the data series in the measurement program section of the GAWSIS station report | JK |  | on |  | 2014-06-28
A2014-08 | Obtain guidance on how to address requests for commercial use of data from EPAC SSC | JK |  | on | Issue has been deposited with EPAC SSC and is in their hands. | 2014-08-29
A2014-10 | Draft an amendment to the GAW data policy requiring the quotation of a data acknowledgment statement for use in publications and request SSC EPAC to endorse it. | JK, MS |  | on | subsumed under A2014-23 | 2014-08-29
A2014-14 | Develop a consistent data quality assessment scheme based on WOUDC approach | MS and TC to coordinate, all WDCs to contribute |  | on | closed, without action (deferred to WMDS) | 2014-10-16
A2014-17 | Confirm with the Secretariat the process of maintaining GAW country contacts in GAWSIS | JK |  | on | Presently administered by Oksana Tarasova | 2014-06-17
A2014-18 | Nominate outstanding contributors for follow-up (with candy) by GAW Secretariat and EPAC SSC chair | All WDCs to send nominations to JK |  | on | No nominations received ;-(
A2014-21 | Schedule next meeting and teleconferences |  |  | on | next telecon scheduled, rolling activity
A2014-23 | Rainer was asked to provide a draft of this numerical QA/QC flagging system. Each WDC should review this draft and send comments to Jörg by 31 July 2014. Jörg will attempt to harmonize these comments into a single ET-WDC response by 23 August 2014. | Input from all, JK to coordinate response | 2014-10-31 | on | closed, without action (deferred to WMDS) | 2014-10-16
A2014-24 | Van will contact Bob Vet about CAPMoN participation in GAW and possible ways to exchange CAPMoN metadata with GAWSIS. | VB | 2014-09-30 | on | CAPMoN considers itself to contribute to GAW. Investigate if an LOA can be signed. Establish technical solutions for metadata exchange (new item A2014-25 | 2014-08-29